## Master
Goal 1: To write $100,000 of commission business in a 12 month snapshot
Goal 2: To write a $20,000 commission case
Goal 3:To increase presence and brand awareness within local business community of agency and value proposition
Objectives: Pre-Pipeline, Scrubber, Critical Path of Pipeline and Sales Process, Developing more first appointments, understanding the 'vital few' of purchasing officers, using LinkedIn and developing 'Event Wizards,'
attending Mixers where buyers congregate, developing SAP's and COI's,
developing a 'JoyPak,' activity metrics
Objective 1: | The Production Engine + Calendar discipline and time management
Objective 2: | Marketspace, Research, Packaging the Approach, 'enabling the assignment of value' and identifiying 'imperfections of fit' nest prospecting within SAP's
Objective 3: | LinkedIn: Profile, testimonials, contacts, Forums, Event Wizards, how to develop introductions from others using LinkedIn, press kit, image package
Objective 4: | JoyPak, Sales Initiative Development, developing more first appointments, specific mixers to attend where buyers congregate, developing niche specialty
Objective 5: | Pipleline and Activity Metric Reporting
Key Events |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 6 | Week 8 | Week 10 | Week 12 | Week 14 | Week 16 | Week 18 | Week 20 | Week 22 | Week 24 | Week 26 | Totals
Assigned Date Schedule | Owner | Team Members
The Production Engine | David | David/Jonathan/Team Rainmaker
Pre-Pipeline | David | bar: Week 1 to Week 2; Week 26
The Scrubber | David | bar: Week 1 to Week 2; Week 26
The Critical Path | David/Jonathan | bar: Week 1 to Week 4; Week 26
Supporting Tools for the Critical Path | David/Jonathan | bar: Week 1 to Week 4; Week 26
Drip Campaign | David | bar: Week 4; Week 18 to Week 22
Capabilities presentation | Jonathan | bar: Week 4 to Week 8
Marketing Presentation | Jonathan | bar: Week 4 to Week 8
ROI templates | David/Jonathan | bar: Week 4 to Week 8
Service Agreements | David/Jonathan | bar: Week 4 to Week 8
Performance Scorecards | David/Jonathan | bar: Week 4 to Week 8
Using Survey tools | David/Jonathan | bar: Week 4 to Week 8
Calendar discipline/time management | Jonathan/David | bar: Week 1 to Week 3; Week 22 to Week 26
Marketspace.Research/Approach, etc | David/Jonathan | David/Jonathan + Team Rainmaker
Marketspace Overview | David | bar: Week 4
Identifying 'Imperfections of Fit' as good targets | David/Jonathan | bar: Week 4 to Week 6
Enabling the 'Assignment of Value' | Jonathan | bar: Week 6
Packaging the Approach | Jonathan | bar: Week 6 to Week 8
Researching good targets to fit the model | Jonathan | bar: Week 6 to Week 20
Overivew of research tools + usage | David/Jonathan | bar: Week 8 to Week 14
Nest prospecting within alliiance partnerships | Jonathan | bar: Week 8 to Week 14; Week 24 to Week 26
LinkedIn + Packaging + Sales Initiatives | Jonathan | Jonathan & Team Rainmaker
LinkedIn Profile Building | Jonathan | bar: Week 3 to Week 6
LinkedIn testimonials & Event Wizard | Jonathan | bar: Week 3 to Week 6; Week 22 to Week 26
LinkedIn Forums | Jonathan | bar: Week 3 to Week 6
generating introductions from LinkedIn | Jonathan | bar: Week 3 to Week 6; Week 22 to Week 26
Lunch & Learns | David/Jonathan | bar: Week 3 to Week 6
Competitive Analysis - what to look for and use | David | bar: Week 3 to Week 6
QuickLife Intro Webinar | David | David/QuickLife | bar: Week 2 to Week 3
Image Pak | bar: Week 16 to Week 20
Onsite Workshops hosted by alliance partners | Jonathan | bar: Week 3 to Week 6; Week 16 to Week 20
Sales Initiative Development | Jonathan | Jonathan & Team Rainmaker
Developing more first appointments | Jonathan | bar: Week 1 to Week 20
Mixers to Attend - identifying/what to do | Jonathan/David | bar: Week 1 to Week 12
The JoyPak | Jonathan/David | bar: Week 4 to Week 8; Week 22 to Week 26
Finding Where Buyers Congregate | Jonathan | bar: Week 4 to Week 6
Expertise/Niche development | Jonathan
list procurement by niche targets | David/Jonathan | bar: Week 12 to Week 14
Cross sell matrix w/alliance partners | Jonathan/David | bar: Week 16 to Week 20
Pipeline & Activity Metric Reporting | Jonathan | Jonathan/David/Jay
Direct Calls/Emails - Goal | Jonathan |  | 30 | 30 | 30 | 10 | 30 | 30 | 35 | 30 | 30 | 30
Direct Calls - Completed |  |  | 23 | 25 | 20 | 10 | 30 | 30 | 35 | 30 | 30 | 30
Direct Letters - Completed |  |  | 8 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Business Appointments - Goal | Jonathan | bar: Week 1 to Week 16
New Business Appointments - Actual |  |  | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 1 | 1 | 1
Top 25 Prospect List - Goal | Jonathan |  | 10 | 15 | 15 | 20 | 25 | 25 | 25 | 25 | 25 | 25
Top 25 Prospect List - Actual |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Mixers Attended - Goal | Jonathan |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
Mixers Attended - Actual |  |  | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1
COI Developed (Individual) - Goal | Jonathan | bar: Week 1 to Week 16
COI Developed (Individual) - Actual | bar: Week 1 to Week 26
Introductions Obtained - Goal | Jonathan |  | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 1
Introductions Obtained - Actual |  |  | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1
LinkedIn Connections Added |  |  | 4(more pending) | 6 | 4 | 4 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10